## Start here
PM DataLab: Excel practice workbook
Fictional company "Prairie Logistics". All names and figures are invented for practice.
How to use this workbook
1. Read an exercise on the Exercises sheet.
2. Go to the sheet and cell it names. Yellow cells are where your formulas go.
3. Where an exercise says "fill down", write the formula in the first row and copy it down to the last yellow row.
4. Compare with the Answers sheet, or the green cells on "Projects (solved)" and "Tasks (solved)".
Legend
Yellow cell = your input (formula goes here)
Green cell = model answer (formula)
Online version with instant checking: https://pmport.ca/pm-datalab/excel

## Projects
Project ID | Project | Department | Manager ID | Status | Priority | Budget (BAC) | Actual Cost (AC) | % Complete | Planned % | EV | PV | CV | CPI | SPI | RAG | Budget check | Manager
P01 | CRM Upgrade | IT | R01 | In Progress | High | 250000 | 182000 | 68% | 75%
P02 | Data Warehouse Migration | IT | R02 | In Progress | High | 480000 | 265000 | 52% | 55%
P03 | HR Self-Service Portal | HR | R03 | Completed | Medium | 120000 | 128500 | 100% | 100%
P04 | Warehouse Automation | Operations | R02 | In Progress | High | 900000 | 410000 | 40% | 48%
P05 | Customer Feedback Analytics | Marketing | R04 | In Progress | Medium | 95000 | 61000 | 70% | 65%
P06 | Office Relocation | Facilities | R05 | At Risk | Medium | 210000 | 150000 | 55% | 70%
P07 | Cybersecurity Training | IT | R01 | Not Started | Low | 60000 | 0 | 0% | 10%
P08 | Budget Planning Tool | Finance | R04 | Completed | Low | 75000 | 71200 | 100% | 100%
Total
In-progress projects
High-priority budget
Portfolio CPI
Blocked tasks
P04 planned hours
P01 tasks done
Largest project
Note on B13: Exercise 12: Count in-progress projects
Note on B14: Exercise 13: Budget of high-priority projects
Note on B15: Exercise 14: Portfolio CPI
Note on B16: Exercise 15: Blocked tasks
Note on B17: Exercise 16: Planned hours for one project
Note on B18: Exercise 17: Done tasks in a project
Note on B19: Exercise 18: Project with the largest budget
Note on G11: Exercise 9: Total budget
Note on H11: Exercise 10: Total actual cost
Note on I11: Exercise 11: Average % complete
Note on L2: Exercise 1: Earned value (EV)
Note on M2: Exercise 2: Planned value (PV)
Note on N2: Exercise 3: Cost variance (CV)
Note on O2: Exercise 4: CPI with IFERROR
Note on P2: Exercise 5: Schedule performance (SPI)
Note on Q2: Exercise 6: RAG status
Note on R2: Exercise 7: Budget check
Note on S2: Exercise 8: Manager name lookup

## Tasks
Task ID | Project ID | Task | Phase | Planned Hours | Actual Hours | Status | Owner ID | Hours variance % | Labour cost
T01 | P01 | Gather CRM requirements | Planning | 120 | 135 | Done | R06
T02 | P01 | Configure CRM modules | Execution | 400 | 380 | Done | R08
T03 | P01 | Migrate customer data | Execution | 240 | 210 | In Progress | R07
T04 | P01 | User acceptance testing | Testing | 160 | 60 | In Progress | R09
T05 | P01 | Train sales team | Closing | 80 | 0 | Not Started | R01
T06 | P02 | Assess source systems | Planning | 150 | 170 | Done | R06
T07 | P02 | Design warehouse model | Planning | 200 | 230 | Done | R07
T08 | P02 | Build ETL pipelines | Execution | 600 | 340 | In Progress | R07
T09 | P02 | Build Power BI reports | Execution | 300 | 40 | In Progress | R10
T10 | P02 | Data validation | Testing | 180 | 0 | Not Started | R09
T11 | P03 | Map HR processes | Planning | 90 | 100 | Done | R06
T12 | P03 | Build portal | Execution | 320 | 365 | Done | R08
T13 | P03 | Test and launch portal | Testing | 110 | 120 | Done | R09
T14 | P04 | Vendor selection | Planning | 160 | 150 | Done | R02
T15 | P04 | Install conveyor system | Execution | 800 | 420 | In Progress | R05
T16 | P04 | Integrate warehouse software | Execution | 500 | 150 | Blocked | R08
T17 | P04 | Safety certification | Testing | 120 | 0 | Not Started | R09
T18 | P04 | Go-live and handover | Closing | 90 | 0 | Not Started | R02
T19 | P05 | Define feedback KPIs | Planning | 60 | 55 | Done | R10
T20 | P05 | Build survey data pipeline | Execution | 200 | 190 | Done | R07
T21 | P05 | Sentiment dashboard | Execution | 180 | 120 | In Progress | R10
T22 | P05 | Present insights | Closing | 40 | 0 | Not Started | R04
T23 | P06 | Find new office space | Planning | 80 | 95 | Done | R05
T24 | P06 | Fit-out and furniture | Execution | 300 | 210 | Blocked | R05
T25 | P06 | Move IT equipment | Execution | 120 | 0 | Not Started | R08
T26 | P06 | Staff move and closeout | Closing | 60 | 0 | Not Started | R05
T27 | P07 | Design training content | Planning | 100 | 0 | Not Started | R06
T28 | P07 | Deliver training sessions | Execution | 150 | 0 | Not Started | R01
T29 | P08 | Gather budget requirements | Planning | 70 | 65 | Done | R06
T30 | P08 | Build budget tool | Execution | 260 | 250 | Done | R08
T31 | P08 | Finance team rollout | Closing | 50 | 48 | Done | R04
Note on I2: Exercise 19: Hours variance %
Note on J2: Exercise 20: Labour cost per task

## Resources
Resource ID | Name | Role | Department | Hourly Rate
R01 | Aisha Khan | Project Manager | PMO | 85
R02 | Daniel Wong | Project Manager | PMO | 90
R03 | Maria Lopez | Project Manager | PMO | 80
R04 | Priya Patel | Project Manager | PMO | 82
R05 | Tom Becker | Project Coordinator | Facilities | 55
R06 | Leila Haddad | Business Analyst | IT | 70
R07 | Jonas Meyer | Data Engineer | IT | 78
R08 | Grace Kim | Developer | IT | 75
R09 | Omar Siddiqui | QA Analyst | IT | 62
R10 | Chloe Martin | Data Analyst | Marketing | 68

## Risks
Risk ID | Project ID | Description | Probability | Impact Cost | Status | Owner ID
K01 | P01 | Data quality issues delay migration | 60% | 40000 | Open | R07
K02 | P01 | Sales team resists new CRM | 40% | 25000 | Open | R01
K03 | P02 | Source system access delayed | 50% | 60000 | Open | R02
K04 | P02 | ETL performance below target | 30% | 45000 | Open | R07
K05 | P03 | Payroll integration defects | 20% | 15000 | Closed | R08
K06 | P04 | Conveyor delivery delayed by supplier | 70% | 150000 | Open | R02
K07 | P04 | Software integration vendor unavailable | 50% | 90000 | Open | R08
K08 | P05 | Low survey response rate | 40% | 10000 | Open | R10
K09 | P06 | Lease signing delayed | 30% | 50000 | Closed | R05
K10 | P06 | Furniture supplier backorder | 60% | 35000 | Open | R05
K11 | P07 | Low training attendance | 50% | 8000 | Open | R01
K12 | P08 | Finance users reject new tool | 20% | 12000 | Closed | R04

## Exercises
# | Exercise | Sheet | Cell | Fill down to | Instructions
1 | Earned value (EV) | Projects | L2 | row 9 | In L2, calculate Earned Value for the first project: EV = Budget × % Complete. Your formula must still work when filled down to row 9.
2 | Planned value (PV) | Projects | M2 | row 9 | In M2, calculate Planned Value: PV = Budget × Planned %. It must work when filled down.
3 | Cost variance (CV) | Projects | N2 | row 9 | In N2, calculate Cost Variance: CV = EV − AC. Calculate EV inside the formula (do not refer to L2). Negative means over budget.
4 | CPI with IFERROR | Projects | O2 | row 9 | In O2, calculate the Cost Performance Index: CPI = EV ÷ AC. One project has no cost yet, which causes a #DIV/0! error. Wrap the formula so it shows 0 instead.
5 | Schedule performance (SPI) | Projects | P2 | row 9 | In P2, calculate SPI = EV ÷ PV, which simplifies to % Complete ÷ Planned %. If Planned % is 0, show 1.
6 | RAG status | Projects | Q2 | row 9 | In Q2, return a RAG status from SPI: "Green" if Planned % is 0 or SPI ≥ 0.95, "Amber" if SPI ≥ 0.85, otherwise "Red".
7 | Budget check | Projects | R2 | row 9 | In R2, show "Over budget" when Actual Cost is greater than Budget, otherwise "Within budget".
8 | Manager name lookup | Projects | S2 | row 9 | In S2, look up the manager's name from the Resources sheet (Resources!A2:E11) using the Manager ID in D2. Lock the lookup range with $ so it does not move when filled down.
9 | Total budget | Projects | G11 |  | In G11, add up the budgets of all eight projects (G2 to G9).
10 | Total actual cost | Projects | H11 |  | In H11, add up the actual cost of all projects.
11 | Average % complete | Projects | I11 |  | In I11, calculate the average % complete across the projects.
12 | Count in-progress projects | Projects | B13 |  | In B13, count how many projects have the status "In Progress".
13 | Budget of high-priority projects | Projects | B14 |  | In B14, add up the budget of projects whose priority is "High".
14 | Portfolio CPI | Projects | B15 |  | In B15, calculate the CPI of the whole portfolio: total EV ÷ total AC. Total EV is the sum of Budget × % Complete for every project, in one formula.
15 | Blocked tasks | Projects | B16 |  | In B16, count the tasks on the Tasks sheet with status "Blocked" (Tasks!G2:G32).
16 | Planned hours for one project | Projects | B17 |  | In B17, add up the planned hours (Tasks!E2:E32) of all tasks for project "P04" (Tasks!B2:B32).
17 | Done tasks in a project | Projects | B18 |  | In B18, count tasks that belong to project "P01" and have status "Done".
18 | Project with the largest budget | Projects | B19 |  | In B19, return the name of the project with the largest budget, using INDEX and MATCH (no typing the name).
19 | Hours variance % | Tasks | I2 | row 32 | On the Tasks sheet, in I2, calculate the hours variance as a fraction: (Actual Hours − Planned Hours) ÷ Planned Hours. It must work when filled down to row 32.
20 | Labour cost per task | Tasks | J2 | row 32 | On the Tasks sheet, in J2, calculate labour cost: Actual Hours × the owner's hourly rate, looked up from Resources (rate is column 5 of Resources!A2:E11).

## Answers
# | Exercise | Cell | Model formula (type = first)
1 | Earned value (EV) | Projects!L2 | G2*I2
2 | Planned value (PV) | Projects!M2 | G2*J2
3 | Cost variance (CV) | Projects!N2 | G2*I2-H2
4 | CPI with IFERROR | Projects!O2 | IFERROR(G2*I2/H2,0)
5 | Schedule performance (SPI) | Projects!P2 | IF(J2=0,1,I2/J2)
6 | RAG status | Projects!Q2 | IF(J2=0,"Green",IF(I2/J2>=0.95,"Green",IF(I2/J2>=0.85,"Amber","Red")))
7 | Budget check | Projects!R2 | IF(H2>G2,"Over budget","Within budget")
8 | Manager name lookup | Projects!S2 | VLOOKUP(D2,Resources!$A$2:$E$11,2,FALSE)
9 | Total budget | Projects!G11 | SUM(G2:G9)
10 | Total actual cost | Projects!H11 | SUM(H2:H9)
11 | Average % complete | Projects!I11 | AVERAGE(I2:I9)
12 | Count in-progress projects | Projects!B13 | COUNTIF(E2:E9,"In Progress")
13 | Budget of high-priority projects | Projects!B14 | SUMIF(F2:F9,"High",G2:G9)
14 | Portfolio CPI | Projects!B15 | SUMPRODUCT(G2:G9,I2:I9)/SUM(H2:H9)
15 | Blocked tasks | Projects!B16 | COUNTIF(Tasks!G2:G32,"Blocked")
16 | Planned hours for one project | Projects!B17 | SUMIFS(Tasks!E2:E32,Tasks!B2:B32,"P04")
17 | Done tasks in a project | Projects!B18 | COUNTIFS(Tasks!B2:B32,"P01",Tasks!G2:G32,"Done")
18 | Project with the largest budget | Projects!B19 | INDEX(B2:B9,MATCH(MAX(G2:G9),G2:G9,0))
19 | Hours variance % | Tasks!I2 | (F2-E2)/E2
20 | Labour cost per task | Tasks!J2 | F2*VLOOKUP(H2,Resources!$A$2:$E$11,5,FALSE)
Formulas are shown without the leading = so you can read them. Type = and then the formula. Live versions are on the "(solved)" sheets.

## Projects (solved)
Project ID | Project | Department | Manager ID | Status | Priority | Budget (BAC) | Actual Cost (AC) | % Complete | Planned % | EV | PV | CV | CPI | SPI | RAG | Budget check | Manager
P01 | CRM Upgrade | IT | R01 | In Progress | High | 250000 | 182000 | 68% | 75% | 170000 | 187500 | -12000 | 0.93407 | 0.90667 | Amber | Within budget | Aisha Khan
P02 | Data Warehouse Migration | IT | R02 | In Progress | High | 480000 | 265000 | 52% | 55% | 249600 | 264000 | -15400 | 0.94189 | 0.94545 | Amber | Within budget | Daniel Wong
P03 | HR Self-Service Portal | HR | R03 | Completed | Medium | 120000 | 128500 | 100% | 100% | 120000 | 120000 | -8500 | 0.93385 | 1 | Green | Over budget | Maria Lopez
P04 | Warehouse Automation | Operations | R02 | In Progress | High | 900000 | 410000 | 40% | 48% | 360000 | 432000 | -50000 | 0.87805 | 0.83333 | Red | Within budget | Daniel Wong
P05 | Customer Feedback Analytics | Marketing | R04 | In Progress | Medium | 95000 | 61000 | 70% | 65% | 66500 | 61750 | 5500 | 1.0902 | 1.0769 | Green | Within budget | Priya Patel
P06 | Office Relocation | Facilities | R05 | At Risk | Medium | 210000 | 150000 | 55% | 70% | 115500 | 147000 | -34500 | 0.77 | 0.78571 | Red | Within budget | Tom Becker
P07 | Cybersecurity Training | IT | R01 | Not Started | Low | 60000 | 0 | 0% | 10% | 0 | 6000 | 0 | 0 | 0 | Red | Within budget | Aisha Khan
P08 | Budget Planning Tool | Finance | R04 | Completed | Low | 75000 | 71200 | 100% | 100% | 75000 | 75000 | 3800 | 1.0534 | 1 | Green | Within budget | Priya Patel
Total | [5 empty] | 2190000 | 1267700 | 60.62%
In-progress projects | 4
High-priority budget | 1630000
Portfolio CPI | 0.91236
Blocked tasks | 2
P04 planned hours | 1670
P01 tasks done | 2
Largest project | Warehouse Automation

## Tasks (solved)
Task ID | Project ID | Task | Phase | Planned Hours | Actual Hours | Status | Owner ID | Hours variance % | Labour cost
T01 | P01 | Gather CRM requirements | Planning | 120 | 135 | Done | R06 | 12.5% | 9450
T02 | P01 | Configure CRM modules | Execution | 400 | 380 | Done | R08 | -5% | 28500
T03 | P01 | Migrate customer data | Execution | 240 | 210 | In Progress | R07 | -12.5% | 16380
T04 | P01 | User acceptance testing | Testing | 160 | 60 | In Progress | R09 | -62.5% | 3720
T05 | P01 | Train sales team | Closing | 80 | 0 | Not Started | R01 | -100% | 0
T06 | P02 | Assess source systems | Planning | 150 | 170 | Done | R06 | 13.33% | 11900
T07 | P02 | Design warehouse model | Planning | 200 | 230 | Done | R07 | 15% | 17940
T08 | P02 | Build ETL pipelines | Execution | 600 | 340 | In Progress | R07 | -43.33% | 26520
T09 | P02 | Build Power BI reports | Execution | 300 | 40 | In Progress | R10 | -86.67% | 2720
T10 | P02 | Data validation | Testing | 180 | 0 | Not Started | R09 | -100% | 0
T11 | P03 | Map HR processes | Planning | 90 | 100 | Done | R06 | 11.11% | 7000
T12 | P03 | Build portal | Execution | 320 | 365 | Done | R08 | 14.06% | 27375
T13 | P03 | Test and launch portal | Testing | 110 | 120 | Done | R09 | 9.091% | 7440
T14 | P04 | Vendor selection | Planning | 160 | 150 | Done | R02 | -6.25% | 13500
T15 | P04 | Install conveyor system | Execution | 800 | 420 | In Progress | R05 | -47.5% | 23100
T16 | P04 | Integrate warehouse software | Execution | 500 | 150 | Blocked | R08 | -70% | 11250
T17 | P04 | Safety certification | Testing | 120 | 0 | Not Started | R09 | -100% | 0
T18 | P04 | Go-live and handover | Closing | 90 | 0 | Not Started | R02 | -100% | 0
T19 | P05 | Define feedback KPIs | Planning | 60 | 55 | Done | R10 | -8.333% | 3740
T20 | P05 | Build survey data pipeline | Execution | 200 | 190 | Done | R07 | -5% | 14820
T21 | P05 | Sentiment dashboard | Execution | 180 | 120 | In Progress | R10 | -33.33% | 8160
T22 | P05 | Present insights | Closing | 40 | 0 | Not Started | R04 | -100% | 0
T23 | P06 | Find new office space | Planning | 80 | 95 | Done | R05 | 18.75% | 5225
T24 | P06 | Fit-out and furniture | Execution | 300 | 210 | Blocked | R05 | -30% | 11550
T25 | P06 | Move IT equipment | Execution | 120 | 0 | Not Started | R08 | -100% | 0
T26 | P06 | Staff move and closeout | Closing | 60 | 0 | Not Started | R05 | -100% | 0
T27 | P07 | Design training content | Planning | 100 | 0 | Not Started | R06 | -100% | 0
T28 | P07 | Deliver training sessions | Execution | 150 | 0 | Not Started | R01 | -100% | 0
T29 | P08 | Gather budget requirements | Planning | 70 | 65 | Done | R06 | -7.143% | 4550
T30 | P08 | Build budget tool | Execution | 260 | 250 | Done | R08 | -3.846% | 18750
T31 | P08 | Finance team rollout | Closing | 50 | 48 | Done | R04 | -4% | 3936